SHDT

Build Order & Roadmap

Sequenced plan from foundations through hero features

Prepared for: Sean O’Connor

Author: Claude (Opus 4.7)

Date: 29 April 2026

Scope: Sequenced build plan covering foundations, Azure deployment, domain credibility features, IoT scaffolding and hero features. Treats SHDT as a real product, not a portfolio piece.

# 1. Executive summary

This plan sequences 24 work items across five phases over roughly 14 weeks. Three principles drive the order. Foundations first — the codebase needs tests, observability, and a deployment story before substantial new features land, otherwise tech debt compounds. Domain credibility before wow factor — anyone in housing judges the basics first (compliance, TSMs, Awaab’s Law), so those land before the more visually striking features. IoT scaffolding before vendor lands — building the data model, ingestion endpoint and time-series infrastructure before the IoT solution is connected means integration is a connector swap, not a project.

### Phase summary

| Phase | Weeks | Theme | Outcome |
| --- | --- | --- | --- |
| 1 | 1–3 | Foundations | Codebase is tested, observable, and structurally clean enough to evolve. |
| 2 | 4–5 | Azure deployment | SHDT runs in Azure with the same data and behaviour as local; CI/CD pushes from main. |
| 3 | 6–8 | Domain credibility | Compliance, TSM and Awaab’s Law surfaces; damp-and-mould risk model with explainability. |
| 4 | 9–10 | IoT scaffolding | Sensor data model + ingestion + live overlay on the digital twin, ready for vendor connect. |
| 5 | 11–14 | Hero features | Natural-language portfolio chat, climate adaptation, voice-to-work-order, board-pack PDF. |

# 2. Phase 1 — Foundations (weeks 1–3)

The codebase has the breadth, but the structural and observability foundations have not caught up. Phase 1 makes everything that follows safer and faster.

1. Split App.tsx and analytics_service.py   (~2 days)

Deliverable: One file per Insights tab under client/src/pages/insights/, one file per Strategic Insight under server/services/insights/, with small registries the routers walk.

Depends on: Test scaffolding (item 2) — refactor first without tests is risky.

Definition of done: App.tsx < 600 lines; analytics_service.py < 400 lines; behaviour parity verified by tests; no merge conflicts on related branches.

2. Pytest + Vitest + GitHub Actions CI   (~3 days)

Deliverable: pytest fixtures and conftest for backend (with a Dockerised Postgres in CI); Vitest with @testing-library/react for the frontend; GitHub Actions running lint, typecheck and tests on every PR.

Definition of done: A trivial PR fails CI if it breaks tests or types; coverage shows for backend; build artifacts produced.

3. /healthz, /readyz and structured JSON logging   (~½ day)

Deliverable: /healthz (liveness), /readyz (DB ping), request_id middleware, JSON formatter, log fields ready for Application Insights ingestion.

Definition of done: Probes return 200 only when the app and dependencies are healthy; every log line carries request_id, route, status, latency_ms, user_id when authenticated.

4. Dead-code cleanup   (~½ day)

Deliverable: Either reinstate Scenarios deliberately or remove server/routers/scenarios.py + client/src/pages/ScenarioPlanner.tsx. Remove server/services/enrichment/monitor.py (broken import). Resolve duplicate database/migrations/004_enrichment*.sql.

Definition of done: Repo grep shows no references to deleted modules; migrations apply cleanly on a fresh database.

5. Alembic for migrations   (~½ day)

Deliverable: Replace ad-hoc SQL files with Alembic. Baseline current schema; existing 002–011 migrations imported as versioned revisions.

Depends on: Item 4 (resolve duplicate 004_enrichment).

Definition of done: `alembic upgrade head` reproduces the production schema on an empty database; downgrade to base works; new migrations are auto-generated.

6. SecretsProvider + Storage abstractions   (~1 day)

Deliverable: A `SecretsProvider` interface with LocalDotenv and AzureKeyVault implementations. A `Storage` interface with LocalFilesystem and AzureBlob implementations. All file IO and secret reads go through these.

Definition of done: No raw os.environ.get() outside the SecretsProvider; no open()/read of bulk data outside the Storage interface; switching providers via env var requires no code changes.

# 3. Phase 2 — Azure deployment (weeks 4–5)

Treats the migration as a single coherent piece of work rather than a scatter of small ports. The codebase changes are minimal; the infrastructure work is moderate.

7. Multi-stage Docker images   (~1 day)

Deliverable: Production-grade Dockerfiles for backend (python:3.11-slim, multi-stage, non-root user) and frontend (node build → nginx serve). Same images run via docker-compose.prod.yml locally and in Azure.

Depends on: Item 6 (config-via-env)

Definition of done: docker-compose -f docker-compose.prod.yml up boots a working stack; images < 500 MB; tagged versions push to a registry (GHCR or ACR).

8. Azure Database for PostgreSQL Flexible Server   (~1 day)

Deliverable: Flexible Server provisioned with Geospatial extension; init.sql + Alembic migrations applied; connection string in Key Vault.

Depends on: Item 5 (Alembic), Item 6 (Key Vault)

Definition of done: Backend connects to Azure DB from Container Apps; PostGIS spatial queries return identical results to local.

9. Container Apps + Static Web Apps + Application Insights   (~2 days)

Deliverable: Backend deployed to Azure Container Apps (auto-scale 1–N), frontend to Azure Static Web Apps. Application Insights collects traces, exceptions and dependency calls. Custom domain and TLS certs configured.

Depends on: Items 3, 7, 8

Definition of done: A request to https://app.shdt.example.com hits the SPA, calls the API, returns property data, and shows up in App Insights with full traces.

10. Blob Storage for file assets   (~1 day)

Deliverable: Excel uploads, OS UPRN cache, IoD CSV downloads, EPC bulk files all routed through the Storage abstraction backed by Azure Blob in production.

Depends on: Item 6

Definition of done: No local filesystem reads in production code paths; uploads survive container restarts; the OS UPRN cache is shared across instances.

11. GitHub Actions CD   (~1 day)

Deliverable: Push to `main` builds backend and frontend images, pushes to ACR/GHCR, runs migrations against staging, deploys to Container Apps with revision-based blue/green.

Depends on: Items 2, 9

Definition of done: Merging a PR to main results in a deployed change in staging within 10 minutes; rollback is one click.

# 4. Phase 3 — Domain credibility (weeks 6–8)

Four features that change how the project reads to anyone in the housing sector. Compliance, TSMs and Awaab’s Law are table stakes for anyone judging this against a real housing system; the damp-and-mould risk model is the differentiator.

12. Statutory compliance dashboard   (~2 days)

Deliverable: Five tiles — gas (CP12), electrical (EICR), Fire Risk Assessment, asbestos register, water hygiene/Legionella. Per-property next-due dates, RAG status, drill-down list, "Generate compliance pack" PDF.

Definition of done: Compliance page renders portfolio totals; clicking a tile filters the property list; PDF export contains every property with its compliance status.

13. Tenant Satisfaction Measures dashboard   (~2 days)

Deliverable: All 22 TSMs with the regulator’s exact codes (TP01–TP12, RP01–RP02, BP01, CH01–CH02, NM01, AS01). Synthetic survey data initially, structured for swap-in real data later.

Definition of done: TSM page renders all 22 measures with portfolio scores; export to CSV in the regulator’s submission format.

14. Awaab’s Law caseload board   (~2 days)

Deliverable: Kanban: Reported → Investigated → Repair scheduled → Repaired → Closed. 14-day investigation SLA clock and 7-day emergency repair SLA clock. Breaches escalate as critical Strategic Insights.

Definition of done: Cases auto-update SLA status as time passes; breaches trigger an Insight card; cases link to the property and to the originating complaint.

15. Damp-and-mould risk model with explanation   (~3 days)

Deliverable: Per-property risk score (0–100) computed from EPC + overcrowding + complaint text + heating type + age + ventilation proxy + IoT humidity (when available). Glass-box: every score has an "explanation" panel listing factors and weights.

Depends on: Item 14 (caseload integration), Item 19 (will gain sensor input later)

Definition of done: Risk score column is populated for every property; new map heatmap layer for damp/mould; new Insight card with top-10 highest-risk properties; explanation panel renders in PropertyDetailPanel.

# 5. Phase 4 — IoT scaffolding (weeks 9–10)

Done before the procured IoT solution arrives, so the integration is a vendor connector swap rather than a stand-up project.

16. Sensor data model   (~1 day)

Deliverable: New tables: `sensors` (device_id, property_id FK, vendor, model, location_in_property, installed_at, status), `sensor_readings` (sensor_id, ts, metric, value, quality). Time-series partitioned by month.

Depends on: Item 5 (Alembic)

Definition of done: Schema applied via Alembic; foreign keys to properties via UPRN; indexes on (sensor_id, ts DESC).

17. Time-series infrastructure   (~2 days)

Deliverable: Enable TimescaleDB on the existing Postgres (sensor_readings becomes a hypertable; continuous aggregates for hourly/daily rollups). Document the migration path to Azure Data Explorer for very high volume.

Depends on: Item 16

Definition of done: Inserts at 1k readings/second do not affect query latency; hourly aggregate query returns in <100ms; retention policy automatically drops raw data older than 90 days while keeping aggregates.

18. Vendor-agnostic ingestion endpoint   (~1 day)

Deliverable: POST /api/iot/readings webhook accepting batched readings. Authenticated by per-vendor API key. Validates UPRN, sensor exists, metric in allow-list. Writes to sensor_readings.

Depends on: Items 16, 17

Definition of done: A documented OpenAPI spec; rate-limited; rejects unknown sensors; integration tests covering happy path, malformed payload, unknown sensor, replay protection.

19. Live overlay on PropertyViewer3D   (~3 days)

Deliverable: Animate temperature, humidity and CO₂ on the existing 3D model with a 7-day playback slider, served from the readings table via a /api/iot/timeseries endpoint. Seeded with simulated data so the UI works before the vendor is connected.

Depends on: Items 17, 18

Definition of done: Slider scrubs through 7 days; values update in real-time; missing-data periods are visually distinct; legend explains scale.

20. Sensor-driven damp/mould signal   (~1 day)

Deliverable: When humidity > 65% for >12h alongside temperature < 16°C, raise property risk score and create an Awaab’s Law case in "Reported" state.

Depends on: Items 15, 18, 19

Definition of done: A controlled simulation produces a case automatically; the case shows the triggering readings; the property risk score updates within 5 minutes.

# 6. Phase 5 — Hero features (weeks 11–14)

Four features that, well-executed, materially raise the ceiling on what SHDT can credibly claim.

21. "Ask the portfolio" natural-language chat   (~3 days)

Deliverable: A query box that compiles natural language into SQL using Anthropic Claude with function-calling, runs it against a read-only role, and renders the answer as a filterable map view. A "How was this answered?" panel shows the SQL.

Depends on: Items 1, 6 (Secrets)

Definition of done: Twenty test queries return correct answers; rejects DDL/DML; cannot read sensitive PII columns; logs every query for audit.

22. Climate adaptation map layer (UKCP18)   (~3 days)

Deliverable: Layer UKCP18 climate projections for 2030/2050/2080 sea level + flood return periods on the existing EA flood map. Per-property climate-resilience score. Headline KPI: "by 2050, X% of stock has Medium+ exposure".

Definition of done: Map toggle for 2030/2050/2080; per-property score in the detail panel; Insight card for "Stock exposed to sea-level rise by 2050".

23. Voice-to-work-order surveyor capture   (~3 days)

Deliverable: A surveyor mobile route records a 30-second audio note → Whisper transcription → Claude extracts structured fields (UPRN, component, condition 1–5, action) → creates a maintenance_records row.

Depends on: Items 6, 16

Definition of done: A test on five real audio notes correctly populates work orders with >90% field accuracy; surveyor sees a confirmation screen before commit.

24. Board-pack PDF report   (~1 day)

Deliverable: A single-click portfolio report — overview, top 10 risk properties, retrofit priorities, capital programme, compliance status, TSM summary. Branded, A4, exportable to email.

Depends on: Items 12, 13, 15

Definition of done: PDF generated in <30 seconds for a 20K-property portfolio; deterministic output; downloaded with a versioned filename.

# 7. Risks and dependency notes

- Item 1 (refactor) before item 2 (tests) is the single biggest risk in the plan. Resist the temptation. Without test coverage, the split will introduce subtle behaviour drift that is hard to diagnose.

- Items 8–11 (Azure) require Azure credentials, a tenant, and at least an estimate of expected cost. Container Apps + Flexible Server + Static Web Apps is roughly £40–£120 / month at low usage with autoscale-to-zero on the backend.

- Item 17 (TimescaleDB) is supported on Azure Database for PostgreSQL Flexible Server but only on specific extension allow-lists. Verify before committing; the fallback is to keep readings in vanilla Postgres with monthly partitioning.

- Item 21 ("Ask the portfolio") must use a read-only DB role and an allow-list of tables. The provenance toggle is what makes it credible to housing managers — do not skip it.

- Item 22 (UKCP18) source data is large (multi-GB NetCDF). Pre-process locally into a smaller derived dataset (per-LSOA score per scenario per epoch) rather than streaming raw NetCDF in production.

# 8. IoT procurement requirements

Four contractual requirements to insist on with whoever is selected. These are cheap to ask for now and very expensive to retrofit later.

- Insist on direct webhook or REST access to raw readings. Do not accept "vendor dashboard + CSV export" as the integration story.

- UPRN as the device-to-property identifier in the contract. Some vendors use their own internal IDs; resolving those back to UPRN is its own project.

- Per-vendor API key, scoped to /api/iot/readings only. Rotate annually. Log the vendor on every reading.

- Document the sensor calibration regime upfront. Drift on humidity sensors will quietly poison your damp/mould model if not caught.

# 9. Closing thoughts

The plan is sequenced for compounding effect — every phase makes the next phase faster, cheaper or more credible. The single most important decision in the plan is the order of items 1 and 2: tests first, then refactor. That single choice is the difference between a clean evolution and a long debugging tail.

On budget: Phase 1 is mostly local, no extra cost. Phase 2 introduces Azure spend at ~£40–£120 / month for low-load configurations. Phases 3–5 may incur small costs (Anthropic API for natural-language and voice features, possibly a UKCP18 dataset preprocessing pipeline) but nothing that would surprise a normal product budget.